SportX V1

Team Check-In  ·  10 June 2026

1.  Where We Are

| DONE | NOT DONE |
| --- | --- |
| Full landing page, auth flow, all dashboards (player + scout) Basic 4-step onboarding + SportX Score logic Workflow + overview explainer pages Full UI component library Every screen is built. The product looks like a product. | Zero backend — no DB schema, no API routes, no real auth Onboarding is 4 steps; designed flow is 12 (Aadhaar OTP, guardian, stats, match log OCR, fitness, psych test, video AI, coach verification) AI modules (video analysis + psych profiling) — fully specced by Mrigank, not coded yet Scout search + player discovery not built Coach verification + profile strength + badges not built |

2.  Timeline to V1

| Phase | Deliverable | Duration | Owner |
| --- | --- | --- | --- |
| 1 | Supabase schema + auth + basic onboarding saves real data | 2 weeks | Hritvik |
| 2 | Full 12-step onboarding (Aadhaar, stats, match log, fitness) | 3 weeks | Hritvik |
| 3 | Video analysis pipeline (FastAPI + Gemini) live end-to-end | 2 weeks | Mrigank |
| 4 | Psych profiling pipeline live end-to-end | 1 week | Mrigank |
| 5 | Coach verification + profile strength + badges | 1 week | Hritvik |
| 6 | Scout search (tag-based filter) + player discovery | 1 week | Hritvik + Harshit |
| 7 | QA + bug fixes + staging deployment | 1 week | All |
| Total | Target: Late August 2026 | ~11 weeks |  |

3.  Blockers  —  Resolve Now

- No company entity / bank account — Surepass + Gemini API require a registered business. Action: Mausi to advise LLP vs Pvt Ltd timeline.

- Aadhaar eKYC vendor approval — 2–4 week lead time after entity formed. Needs to start in parallel with development immediately.

- ACSI-28 commercial licensing unresolved — Mrigank to send licensing inquiry this week. Fallback: OMSAT-3*.

- Backend capacity undefined — Mrigank's committed hours/week needed before Phase 3–4 can be planned.

- No Figma design system — Harshit to deliver component library matching current UI by end of next week.

4.  Decisions Needed Today

- Entity type (LLP or Pvt Ltd) and formation timeline  (Mausi)

- V1 scope: full 12-step onboarding now, or 6-step launch + Aadhaar/psych/video in V1.1?  (All)

- Mrigank committed hours per week — confirm the number  (Mrigank)

- Tag-based player filtering (not semantic search) confirmed for V1  (Close this decision)

5.  Status by Person

| Hritvik | Frontend complete. Full focus shifts to backend + Supabase integration. |
| --- | --- |
| Mrigank | Both engineering specs done. Move from docs to working FastAPI code. |
| Harshit | Deliver Figma system for existing UI. Design QA role going forward. |
| Mausi | Unblock: entity formation, Aadhaar vendor onboarding, DPDPA legal review. |